Lab Planning

Name of Teacher: Vishal Tank 							Date: 01/05/2020

Subject: EC346 Group Project-1							Semester: 6

| Sr.No. | MONTH | DAYS | TOPICS |
| --- | --- | --- | --- |
| 1 | June-July | 29-04 | Introduction to subject sharing some ideas of projects. (1) The implementation of practical problem in testing of electronics or communication equipments (2) The microprocessor/microcontroller based applications (3) simulation of problem statement/research paper using software like MATLAB, C and Python etc. |
| 2 | July | 06-11 | Group identification and Brain storming before finalizing definition of project (Max 2 students per group ,in case of complex project 3 students are allowed ) |
| 3 |  | 13-18 | Student need to submit abstract of project in hardcopy to teachers. |
| 4 |  | 20-25 | 1st Internal Presentation and feedback of teachers |
| 5 | July- August | 27-01 | Modification based in project based on feedback |
| 6 | August | 03-08 | Working on projects and Submit Progress Report of Project to teachers-1 |
| 7 |  | 10-15 | Working on projects and Submit Progress Report of Project to teachers-2 |
| 8 |  | 17-22 | Working on projects and Submit Progress Report of Project to teachers-3 |
| 9 |  | 24-29 | Working on projects and Submit Progress Report of Project to teachers-4 |
| 10 | August-September | 31-05 | 2nd Internal Presentation and feedback of teachers |
| 11 | September | 07-12 | Working on projects and Submit Progress Report of Project to teachers-5 |
| 12 |  | 14-19 | Working on projects and Submit Progress Report of Project to teachers-6 |
| 13 |  | 21-26 | Working on projects and Submit Progress Report of Project to teachers-7 |
| 14 | Sept-Oct | 28-03 | Working on projects and Submit Progress Report of Project to teachers-8 |
| `5 | October | 05-10 | Demonstration of Project. |
| `6 |  | 12-17 | Project Report explanation |
| `7 |  | 19-24 | Preparation of project report-1 |
| 18 |  | 26-31 | Preparation of Project Report-2 and correction by the teachers |
| 19 | November | 02-07 | Final Submission-1 |
| 20 |  | 09-13 | Final Submission-2 |